## Tabelle1
|  | start date | Duration | end date
A- PROJECT STUDY | Users’ needs | 2022-08-29 | 4 | 2022-09-02
| POC roadmap | 2022-09-02 | 10 | 2022-09-12
| Code example and prototype relative to the POC | 2022-09-12 | 25 | 2022-10-07
B- MODELING | System specification | 2022-10-07 | 5 | 2022-10-12
| System design | 2022-10-12 | 3 | 2022-10-15
| Traceability and allocation | 2022-10-15 | 4 | 2022-10-19
| Test mode | 2022-10-19 | 2 | 2022-10-21
C-HARDWARE CONCEPTION | NFC system | 2022-10-21 | 4 | 2022-10-25
| Motors prototyping | 2022-10-25 | 1 | 2022-10-26
| Presence detection prototyping | 2022-10-26 | 2 | 2022-10-28
D- PROGRAMMING | Firmware programming | 2022-10-28 | 21 | 2022-11-18
| Manage interruption | 2022-11-18 | 7 | 2022-11-25
| API to be used by the matching controller program | 2022-11-25 | 3 | 2022-11-28
E- UNIT TESTING | Firmware testing with code coverage | 2022-11-28 | 25 | 2022-12-23
F- SECURITY | Electrical and Material safety | 2022-12-23 | 14 | 2023-01-06
| Data availability and safety | 2023-01-06 | 7 | 2023-01-13
G- DELIVERY | Packaging | 2023-01-13 | 17 | 2023-01-30
0
0
0

## COÛT
| Tâches | Interveneant |  | Temps (J/H) |  | Coût (€) | Coût horaire | 15
A- PROJECT STUDY | Users’ needs | TLM | 2022-08-29 | 4 | 2022-09-02 | 420 | Coût JH | 105
| POC roadmap | RN, AM | 2022-09-02 | 10 | 2022-09-12 | 1050
| Code example and prototype relative to the POC | DA, AM, R, AA | 2022-09-12 | 25 | 2022-10-07 | 2625
B- MODELING | System specification | DA | 2022-10-07 | 5 | 2022-10-12 | 525
| System design | DA | 2022-10-12 | 3 | 2022-10-15 | 315
| Traceability and allocation | TLM | 2022-10-15 | 4 | 2022-10-19 | 420
| Test mode | TLM | 2022-10-19 | 2 | 2022-10-21 | 210
C-HARDWARE CONCEPTION | NFC system | DA, AM | 2022-10-21 | 4 | 2022-10-25 | 420
| Motors prototyping | DA, AM, R, AA, RN | 2022-10-25 | 1 | 2022-10-26 | 105
| Presence detection prototyping | DA, R, AM | 2022-10-26 | 2 | 2022-10-28 | 210
D- PROGRAMMING | Firmware programming | TLM | 2022-10-28 | 21 | 2022-11-18 | 2205
| Manage interruption |  | 2022-11-18 | 7 | 2022-11-25 | 735
| API to be used by the matching controller program | DA | 2022-11-25 | 3 | 2022-11-28 | 315
E- UNIT TESTING | Firmware testing with code coverage | AM | 2022-11-28 | 25 | 2022-12-23 | 2625
F- SECURITY | Electrical and Material safety | DA, AM, R, AA | 2022-12-23 | 14 | 2023-01-06 | 1470
| Data availability and safety | DA | 2023-01-06 | 7 | 2023-01-13 | 735
G- DELIVERY | Packaging | TLM | 2023-01-13 | 17 | 2023-01-30 | 1785
TOTAL |  |  |  | 154 |  | 16170